## Sheet1
CONTROLO DO PROJETO E GESTÃO DO ESFORÇO E DA PRODUÇÃO DA EQUIPA
EQUIPA: |  |  | DATA DE REVISÃO DO PLANO: | [5 empty] | TOTAL: |  |  |  | 1025 |  |  | H
GREENWAY |  |  | VERSÃO |  | DATA: |  |  |  | MAX.: |  |  |  | 2940 |  |  | H | ECTS |  | 15 | H-ECTS | 28 | EQUIPA |  | 7 |  | TX FOLGA | 0.325
|  |  | 2 |  | 2024-06-23 |  |  |  | EFECT. |  |  |  | 1984.5 |  |  | H | Nota: Margem de 33% de não produtividade efectiva
Cristiano Bucur |  |  | Aluno Nº |  | 62444 |  |  |  | CONTROLO DE PRODUTIVIDADE: | [6 empty] | REF.
Guilherme Matos |  |  | Aluno Nº |  | 62863 |  |  |  | MÉTRICAS |  |  |  | SEMANA |  | 1 |  | OBS)
Luís Lamy |  |  | Aluno Nº |  | 62691 |  |  |  | RÁCIO DE PROD. MÉDIA |  |  |  | 68.3333 |  | /S | 116.7353
Margarida Carvalho |  |  | Aluno Nº |  | 60437 |  |  |  | EXECUÇÃO DO ESFORÇO: |  |  |  | 51.65% |  | % | 100%
Miguel Vieira |  |  | Aluno Nº |  | 64320 |  |  |  | ESFORÇO DISPONÍVEL: |  |  |  | 959.5 |  | H | HORAS
OBS: | [8 empty] | OBS)
ATIVIDADES DA EQUIPA |  | MAIO: 6/Maio a 31/Maio | [7 empty] | JUNHO: 3 a 29/JUNHO | [7 empty] | JULHO: 1 a 24 de JULHO | [6 empty] | 25-26/JUL |  |  | CONTR | CONTR
|  | S1 |  | S2 |  | S3 | Apresent. ALFA | S4 |  | S5 | S6 | S7 |  | S8 | Apresent. |  |  | S9 |  | S10 | S11 |  | S12 |  | Apresent. |  |  | HORAS | %
[7 empty] | Piloto ALFA | [7 empty] | Piloto BETA | [9 empty] | Piloto Final
|  | 6/5 |  | 13/5 |  | 20/5 | 23/MAIO | 27/5 |  | 3/6 | 10/6 | 17/6 |  | 24/6 | DELIVERABLES |  |  | 1/7 |  | 8/7 | 15/7 |  | 22/7 |  | DELIVERABLES
TAREFA | DESIGNAÇÃO DA TAREFA
T1 | Generate ideas for the project |  |  | 1 | [10 empty] | 5 | [12 empty] | 6 | 0.3023%
T1.1 | Logo and Product name |  |  | 2 | [23 empty] | 2 | 0.1008%
T1.2 | Project scope |  |  | 5 |  | 2 | [21 empty] | 7 | 0.3527%
T1.3 | Presentation |  |  | 8 |  | 5 | [21 empty] | 13 | 0.6551%
T2 | Basic user operations |  |  | 5 | [23 empty] | 5 | 0.252%
T2.1 | Individual project operations |  |  | 2 | [23 empty] | 2 | 0.1008%
T2.2 | Add new user roles to the project |  |  | 1 |  | 2 | [21 empty] | 3 | 0.1512%
T2.3 | Make validations for the new user roles |  |  | 14 | [23 empty] | 14 | 0.7055%
T3 | BackEnd - Add communities operations |  |  | 16 |  |  |  | 10 | [19 empty] | 26 | 1.31%
T3.1 | Create a basic framework for the communities |  |  | 5 |  | 3 | [21 empty] | 8 | 0.4031%
T3.2 | Create validations for the communities |  |  | 5 | [5 empty] | 2 | 0.5 | 2 |  | 1 | [13 empty] | 10 | 0.5039%
T3.3 | Test community operations |  |  | 6 | [5 empty] | 3 | 3 | 4 |  | 8 | [13 empty] | 24 | 1.209%
T4 | FrontEnd - Carbon foot print calculator |  |  | 6 | [23 empty] | 6 | 0.3023%
T4.1 | Create questions and answers |  |  | 1 |  | 5 | [7 empty] | 3 | [13 empty] | 9 | 0.4535%
T4.2 | Code frontend |  |  | 3 |  | 5 | [7 empty] | 10 | [13 empty] | 18 | 0.907%
T4.3 | Create calculations |  |  | 2 |  | 5 | [7 empty] | 10 | [13 empty] | 17 | 0.8566%
T5 | BackEnd - Add post operations |  |  | 8 | [23 empty] | 8 | 0.4031%
T5.1 | Create a basic framework for community posts |  |  | 4 | [23 empty] | 4 | 0.2016%
T5.2 | Create validations fpr the posts |  |  | 4 | [23 empty] | 4 | 0.2016%
T5.3 | Test post operations | [26 empty] | 0 | 0%
T6 | BackEnd - Add comment operations |  |  | 8 |  | 10 | [21 empty] | 18 | 0.907%
T6.1 | Create a basic framework for post comments |  |  | 4 |  | 8 | [21 empty] | 12 | 0.6047%
T6.2 | Create validations for the comments |  |  | 4 |  | 6 | [21 empty] | 10 | 0.5039%
T6.3 | Test comment operations | [26 empty] | 0 | 0%
T7 | FrontEnd - Google maps integration | [8 empty] | 10 | 6 | 4 |  | 3 | 3.5 | [12 empty] | 23 | 1.159%
T7.1 | Search Google Maps documentation | [6 empty] | 2 |  | 5 | 5 | 5 |  | 8 | 0.5 | [12 empty] | 25 | 1.26%
T7.2 | Implement Google Maps api | [6 empty] | 5 |  | 5 | 3 | 1 |  | 10 | 1 | [12 empty] | 25 | 1.26%
T7.3 | Create UI for google maps routes | [6 empty] | 3 |  | 3 | 2 | 2 |  | 2 | 2 | [12 empty] | 14 | 0.7055%
T8 | Refactor file organization |  |  | 1 |  | 3 | [21 empty] | 4 | 0.2016%
T8.1 | Refactor file structure |  |  | 0.31 |  | 3 | [21 empty] | 3 | 0.1512%
T8.2 | Correct old references |  |  | 0.32 |  | 3 | [21 empty] | 3 | 0.1512%
T8.3 | Test new file system |  |  | 0.33 |  | 3 | [21 empty] | 3 | 0.1512%
T9 | Integration Backend -> Frontend mobile |  |  | 8 |  |  |  | 10 | [19 empty] | 18 | 0.907%
T9.1 | Create react native project |  |  | 2 |  |  |  | 4 | [19 empty] | 6 | 0.3023%
T9.2 | Code sample login screen |  |  | 2 |  |  |  | 3 | [19 empty] | 5 | 0.252%
T9.3 | Connect deployed backend endpoint to frontend |  |  | 4 |  |  |  | 3 | [19 empty] | 7 | 0.3527%
T10 | Front-End Web Integration | [6 empty] | 37 |  | 17 | 19 | 20 |  | 20 | 10 | [12 empty] | 123 | 6.198%
T10.1 | Implement Communities | [6 empty] | 6 |  | 3 | 5 | 1 |  | 4 | 1 | [12 empty] | 20 | 1.008%
T10.2 | Implement Posts | [6 empty] | 6 |  | 5 | 3 | 2 |  | 1 | 2 | [12 empty] | 19 | 0.9574%
T10.3 | Implement Dashboard | [6 empty] | 8 |  | 2 | 3 | 7 |  | 2 | 7 | [12 empty] | 29 | 1.461%
T10.3 | Implement Profile | [6 empty] | 5 |  | 3 | 1 | 1 |  | 3 | 3 | [12 empty] | 16 | 0.8062%
T10.3 | Implement Home Screen | [6 empty] | 2 |  | 1 | 4 | 4 |  | 4 | 0 | [12 empty] | 15 | 0.7559%
T10.3 | Implement Login&Register | [6 empty] | 10 |  | 1 | 1 | 0.5 |  | 0.5 | 0 | [12 empty] | 12 | 0.6047%
T11 | Front-End Mobile Integration | [8 empty] | 15 | 19 | 3 |  | 16.5 | 13 | [12 empty] | 50 | 2.52%
T11.1 | Implement Communities | [8 empty] | 3 | 4 | 1 |  | 1 | 10 | [12 empty] | 19 | 0.9574%
T11.2 | Implement Posts | [8 empty] | 2 | 2 |  |  | 1 | 1 | [12 empty] | 6 | 0.3023%
T11.3 | Implement Profile | [8 empty] | 3 | 3 | 1 |  | 2 | 0 | [12 empty] | 9 | 0.4535%
T11.4 | Implement Home Screen | [8 empty] | 7 | 2 |  |  | 2 | 0 | [12 empty] | 11 | 0.5543%
T11.5 | Implement Carbon Footprint calculator | [8 empty] | 4 | 2 |  |  | 0.5 | 0
T11.6 | Implement google maps navigation | [8 empty] | 2 | 2 |  |  | 6 | 1
T11.7 | Implement Search Flights Screen | [8 empty] | 1 |  | 1 |  | 4 | 1
T11.8 | Implement Login&Register | [8 empty] | 5 | 4 | 0 |  | 0 | 0
T12 | BackEnd - Create MORE Endpoints | [26 empty] | 0 | 0%
T12.1 | List posts | [8 empty] | 5 | 1 | 2 |  | 0 | 0 | [12 empty] | 8 | 0.4031%
T12.2 | List applications | [8 empty] | 1 | 5 | 3 |  | 0 | 0 | [12 empty] | 9 | 0.4535%
T12.3 | Add application | [8 empty] | 4 | 2 | 5 |  | 1 | 0.5 | [12 empty] | 12 | 0.6047%
T12.4 | Post tools(edit, like, comment...) | [6 empty] | 5 |  | 5 | 6 | 12 |  | 10 | 7 | [12 empty] | 45 | 2.268%
T12.5 | List comments | [5 empty] | 3 |  |  | 4 | 2 | 4 |  | 7 | 2 | [12 empty] | 22 | 1.109%
T12.6 | Report comment | [6 empty] | 2 |  | 3 | 4 | 3 |  | 4 | 7 | [12 empty] | 23 | 1.159%
T13 | BackEnd-FrontEnd debug help :) | [26 empty] | 0 | 0%
T13.1 | Backend devs helping frontend devs | [6 empty] | 20 |  | 15 | 11 | 12 |  | 10 | 6 | [12 empty] | 74 | 3.729%
T13.2 | Backend existing Endpoints adjustment | [6 empty] | 5 |  | 5 | 2 | 3 |  | 1 | 2 | [12 empty] | 18 | 0.907%
T13.3 | [27 empty] | 0 | 0%
T14 | Project Management and Communication | [26 empty] | 0 | 0%
T14.1 | Weekly Meeting | 2 |  | 2 |  | 2 | 2 | 3 |  | 2 | 2 | 2 |  | 2 | 3 | [12 empty] | 22 | 1.109%
T14.2 | Daily communication | 3 |  | 3 |  | 3 | 3 | 3 |  | 4 | 4 | 4 |  | 2 | 4 | [12 empty] | 33 | 1.663%
T14.3 | [27 empty] | 0 | 0%
T15 | Presentation - BETA | [26 empty] | 0 | 0%
T15.1 | Build slides | [10 empty] | 4 |  | 3 | [13 empty] | 7 | 0.3527%
T15.2 | Prepare presentation | [12 empty] | 5 | [13 empty] | 5 | 0.252%
T15.3 | Organize presentation | [10 empty] | 2 |  | 1 | [13 empty] | 3 | 0.1512%
T16 | Presentation - ALPHA | [26 empty] | 0 | 0%
T16.1 | Build slides |  |  |  |  | 10 | [5 empty] | 4 |  | 3 | [13 empty] | 17 | 0.8566%
T16.2 | Prepare presentation |  |  |  |  | 5 | [7 empty] | 5 | [13 empty] | 10 | 0.5039%
T16.3 | Organize presentation |  |  |  |  | 5 | [5 empty] | 2 |  | 1 | [13 empty] | 8 | 0.4031%
CONTROLO DE EQUIPA*SEMANA |  | 5 |  | 136 |  | 88 | 8 | 152 |  | 150 | 132 | 115 |  | 151 | 88 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 1025 | 60.29%
REF Média de HORAS EQUIPA * SEMANA |  | 120 |  | 120 |  | 120 | 120 | 120 |  | 120 | 120 | 120 |  | 120 | 120 |  |  | 100 |  | 100 | 100 |  | 100 |  | 100 |  |  | 1700 | 100%
| REF Máx. Esforço Equipa H * Semana | 120 |  | 120 |  | 120 | 120 | 120 |  | 120 | 120 | 120 |  | 120 | 120 |  |  | 120 |  | 120 | 120 |  | 120 |  | 120 |  |  | 1800 | 105.9%
PERFIS DE DESDOBRAMENTO DA EQUIPA
P1 | Project Management | 1 |  | 100 |  | 1 | 5 | 15 |  | 10 | 15 | 9 |  | 7 | 13 | [12 empty] | 176 | 8.869%
P2 | Project Documentation and Dissemination Mat. |  |  | 3 | [10 empty] | 7 | [12 empty] | 10 | 0.5039%
P3 | Specification and Requirements Analyst | [26 empty] | 0 | 0%
P4 | WEB (JS-AJAX) UI Development | 2 |  | 2 | [5 empty] | 20 | 25 | 30 |  | 15 | 20 | [12 empty] | 114 | 5.745%
P5 | Android App / Interface Des. Developer | 1 |  | 1 | [5 empty] | 25 | 15 | 20 |  | 10 | 10 | [12 empty] | 82 | 4.132%
P6 | Google Platform Developer | [8 empty] | 7 | 2 | 9 |  | 12 | 1 | [12 empty] | 31 | 1.562%
P7 | Google Storage Services Developer | [26 empty] | 0 | 0%
P8 | SW Architect / Architectural Requirements | [26 empty] | 0 | 0%
P9 | Unitary / Partial Tests (Tester) | [26 empty] | 0 | 0%
P10 | Integration Tests (Tester) | [26 empty] | 0 | 0%
P11 | SW Architectural Tests / Arch. Requirements | [26 empty] | 0 | 0%
P12 | Final Product Staging Developer | [26 empty] | 0 | 0%
TOTAL: |  | 4 |  | 106 |  | 6 | 5 | 15 |  | 62 | 57 | 68 |  | 44 | 51 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 418 | 21.06%